# Project plan: Sonnendach Lindenhof

Version 1.0, 2 March 2026. Owner: Selin Aydın (technical lead).

## Scope

Rooftop PV on the Grundschule am Lindenhof (roof A) and the Sporthalle Nord (roof B): 198 kWp, 450 x Helion H-440.

Battery storage: 150 kWh in the school basement.

Power purchase agreement: the school buys the solar power at 19.5 ct/kWh for 20 years.

Out of scope for 2026: heat pump pilot for the Freibad Eschenbrück, planned as a follow-up project for autumn 2026.

## Milestones

| Milestone | Target date | Responsible |
| --- | --- | --- |
| Roof lease signed with the municipality | 31 March 2026 | Hanna Vogt |
| Grid connection request sent | 20 March 2026 | Selin Aydın |
| Structural survey of both roofs | 25 April 2026 | Ingenieurbüro Kraft & Partner |
| Installer contract awarded | 30 April 2026 | Board |
| Installation (Whitsun holidays) | 26 May - 5 June 2026 | Lichtbau Solartechnik GmbH |
| Commissioning | 15 June 2026 | Lichtbau / Netze Mittelland |

## Budget

Total budget 312,000 euros, financed by the KlimaKommunal grant (96,000 euros), a bank loan and new member shares.

## Risks

Module delivery times (Helion has quoted 6 weeks).

Load capacity of the sports hall roof is unknown until the structural survey.

The grid operator may require an upgrade of the local transformer station.